Dispatch No. – 355

Date  -  31.01.13

Format

Monthly Progress Report-  Jan. 2013

| S. No. | Activity and Sub-activities | Target (No./Area ha) | Achievements No./Area ha) | Beneficiaries SC/ST | Beneficiaries Other | Total Beneficiaries |
| --- | --- | --- | --- | --- | --- | --- |
| A | Farm Advisory |  |  |  |  |  |
| 1 | Demonstration | 11/37.4 | 11 | 05 | 138 | 135 |
| 1a | Oilseed (ha) | - | - | - | - | - |
| 1b | Pulses (ha) | 3/29.4 | 3/29.4 | 05 | 68 | 73 |
| 1c | Others (ha) | 08/08 | 08 | 04 | 58 |  |
| 2 | Field Days (No.) | - | - | - | - | - |
| 3 | Kisan Mela | - | - | - | - | - |
| 4 | Diagnostic services | 2 | 2 |  |  | Mass |
| 5 | Scientist visit to Farmers field | 5 | 6 | 03 | 29 | 32 |
| 6 | Farmer visit to KVK farm | 4 | 4 | 12 | 80 | 92 |
| 7 | Training for farmers (No.) Total | 5 | 5 | 27 | 128 | 158 |
| 7a | Male (No.) | 5 | 5 | - | 3 | - |
| 7b | Female (No.) | - | - | - | - | - |
| 8 | School Dropouts (No.) Total | - | - | - | - | - |
| 8a | Male (No.) | - | - | - | - | -- |
| 8b | Female (No.) | 1 | 1 | - | 25 | 25 |
| 9 | In-Service Training (no) | 2 | 2 | 21 | 25 | 46 |
| 10 | On farm Testing (No) | 9 | 9 | - | 52 | 52 |
| 11 | Other Extension Activities (No.) total |  |  |  |  |  |
|  | TV Programme | 1 | 1 |  |  | Mass |
|  | News Paper Coverage | 4 | 4 |  |  | Mass |
|  | Popular Article | 1 | 1 |  |  | Mass |
|  | Participating training | 1 | 1 |  |  | 42 |

Name of KVK: Sagar

- Report for January , 2013

1. Report of farmers and rural youth provided Skill development training in the Financial year 2012-13 till the end of July, 2012

| SI.No | State | No. of KVKs | Target of persons to be trained from 2011-2022 | Target for 2012-13 (No of persons) | Achievement by 31.01.2013 (No of persons) | Balance target for 2012-13 (No of persons) | Achievement during the month (January, 2013) (No of persons) | Cumulative achievement for 2012-13 by the end of the reported month (January 2013) |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  |  | Number of Persons | % of annual target |
| 1. | M.P. | Sagar | 3500 | 350 | 217 | 133 | 20 | 217 | 62% |
|  | Total |  | 3500 | 350 | 217 | 133 | 20 | 217 | 62% |

- List of thrust areas of skill development training conducted by KVKs.

Improved nursery management technique, Production Technology of Vermicompost, Fertilizer use efficiency, Ridge and  furrow method of sowing ,  Identification of pest and integrated management, Preparation of pesticide formulation for  various crops, Seed Production Dairy and poultry production , Value addition, post harvest management of fruits and vegetables .

- List of training programme for skill development training of farmers and rural youth with their duration.

- Mango & amla  Preservation.

- Vegetable seed and seedlings treatment by Bio fertilizers/Fungicides.

- Preparation of weedicide / insecticide solution.

- Dairy and poultry production.